Joining a Diocesan CAT

Indicative timeline with outline activities

| Month | Activities and Required actions |  | Term |
| --- | --- | --- | --- |
| 1 | School is in scope within diocesan sequencing plan or school wishes to apply for Stage 1 | Stage 1 approved and school begins engagement with the Trust | T E R M 1 |
| 2 | School proactively engages with the Trust to complete due diligence and conclude ‘soft consultation’ activities |  |  |
| 3 | School submits Stage 2 application to diocesan trustees | Stage 2 consent approved |  |
| 4 | School works with Trust to complete the online DfE application | DfE on line application submitted |  |
| 5 |  |  | T E R M 2 |
| 6 | School application considered by DfE Advisory Board. | School receives DfE approval via letter from DfE. Engage Browne Jacobson LLP |  |
| 7 | Formal Project Planning Meetings (PPM) arranged by DfE commence. Target conversion date agreed | At first PPM target conversion date to be agreed |  |
| 8 | TUPE begins, legal and land related activities commence. PPM’s continue |  |  |
| 9 | TUPE concludes, legal and land documents drafted | LGB reconstitution begins | T E R M 3 |
| 10 | Legal actions concluded. Earliest possible conversion date | School joins Trust on 1st of month |  |
| 11 | Outstanding legal or land issues resolved. Probable conversion date | School joins Trust on 1st of month |  |
| 12 | Reserve conversion date with all matter resolved | School joins Trust on 1st of month |  |

For specific dates relating to Diocesan Trustees meetings and DfE application submissions please refer to the table in the document – ‘Joining a CAT 2023 Guidance’ which can be found here